## Sheet1
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Cross-team AC | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Buyer/Admin, I want to search for a product so that I can find the specific candle scent that I am looking for. | GIVEN that I am logged in as a customer WHEN I am not on the Products page THEN I must see a means to navigate to the Products page. | Pass | Page is listed as Dashboard, not Products as defined | Pass |  | Pass | AP 4/4
| GIVEN that I am not on the Products page WHEN I choose the Products page THEN I am taken to the Products page. | Pass | Page is listed as Dashboard, not Products as defined | Pass |  | Pass | AP 4/4
| GIVEN that I am on the products page WHEN there are products in the inventory THEN I see each product and short description. | Fail | AB; 3/19; As of now users can change the name of a product when only the admin is supposed to when on the details page. | Pass |  | Pass | AP 4/4
As a Buyer I want to add an item to the shopping cart so that I can purchase a product. | GIVEN that a product is not already in my cart WHEN I click a button to add the product THEN the product will be stored and appear in my cart. | Fail | AB; 3/19; Shopping Cart branch not merged | Pass |  | Pass | AP 4/4
| GIVEN that a product is already in my cart WHEN I try to add the product to my cart THEN the button to add the item will be disabled. | Fail | AB; 3/19; Shopping Cart branch not merged | Pass |  | Pass | AP 4/4; shows "product is already in cart" message
| Given that I am on the Products page when there are no products in the inventory I see a message indicating that that there are no products available. | Fail | AB; 3/19; No updating quantity of items | Pass |  | Pass | AP 4/4
As a buyer I want to remove an item from my cart so that I do not keep an item on hold that I don’t plan on purchasing. | GIVEN that I want to remove a product in my cart WHEN I click the button to remove the product THEN the system will remove the item from my cart. | Fail | AB; 3/19; Shopping Cart branch not merged | Pass |  | Pass | AP 4/4
| GIVEN an item is not in my cart WHEN I click the remove product button THEN the button will be disabled. | Fail | AB; 3/19; Shopping Cart branch not merged | Pass | Redundant. There is no "remove item from cart" button outside the cart page. | Pass | AP 4/4; redundant acceptance criterion since there is no such button that can be clicked when an item is not in the shopping cart.
As a user I want to be able to access a shopping cart so that I can continue with my purchases from the e-store. | GIVEN a customer wants to view the products in their cart WHEN they hit the shopping cart button THEN they will be able to see the current products in their cart. | Fail | AB; 3/19; Shopping Cart branch not merged | Pass |  | Pass | AP 4/4
| GIVEN a customer is not on the shopping cart page WHEN they wish to access the shopping cart THEN there will be a button to access the shopping cart. | Fail | AB; 3/19; Shopping Cart branch not merged | Pass |  | Pass | AP 4/4
| GIVEN a customer is not on the shopping cart page WHEN they click the button labeled shopping cart THEN they will be taken to their shopping cart. | Fail | AB; 3/19; Shopping Cart branch not merged | Pass |  | Pass | AP 4/4
As a user I want to be able to log into my account so that I can buy products that I have browsed in the e-store. | GIVEN I want to log into my account WHEN a page appears to login THEN I can enter my username and get taken to the list of products. | Fail | AB; 3/19; Login button works without typing anything | Pass |  | Pass | AP 4/4
| GIVEN I want to use the e-store WHEN the e-store is loaded THEN I am brought to a page asking for my username to login. | Pass |  | Pass |  | Pass | AP 4/4
| GIVEN a user does not yet exist WHEN I try to log in with that username THEN a new user should be added to the system with an empty cart. |  |  | Pass |  | Pass | AP 4/4; taken to user signup page
| GIVEN the username field is blank WHEN I click the log in button THEN I should not be able to log in. |  |  | Pass |  | Pass | AP 4/4
As an owner I want to log in to my e-store with admin access so that I can add/manage enhancements and inventory to my e-store. | GIVEN I want to login as an admin WHEN I enter "admin" under the username section THEN I will be brought to a page where I can edit the inventory of my e-store. | Fail | AB; 3/19; No admin checker implemented | Pass | After logging in, the user is sent to the products page instead of the page to alter inventory. | Pass | AP 4/4; admin is sent directly to inventory list.
As an e-store owner I want to remove an item that is not being sold so that customers remain happy and the website remains accurate. | GIVEN I am logged in as an admin WHEN I no longer want to sell an item THEN I can remove the product from the inventory. | Fail | AB; 3/19; No admin checker implemented | Pass |  | Pass | AP 4/4; can be done using the "x" button
As an e-store owner I want to add a product to the inventory so that customers remain happy and the webpage remains accurate. | GIVEN I am logged in as admin WHEN I want to add a product to the e-store THEN I can update the inventory to add the given product. | Fail | AB; 3/19; No admin checker implemented | Pass |  | Pass | AP 4/4; can add product with default data and edit it later.
As an admin I want to update the status of current products so that the quantities stay up to date and customers can purchase products that are in stock. | GIVEN I am logged in as admin WHEN I receive more stock for an item THEN I can edit the quantity of the candle listed in the e-store. | Fail | AB; 3/19; No admin checker implemented | Pass |  | Pass | AP 4/4
| GIVEN I am logged in as admin WHEN an existing product needs to be edited THEN I will have access to edit the name, quantity and price of the product. | Fail | AB; 3/19; No admin checker implemented | Pass |  | Pass | AP 4/4
As a user I want to logout of my account so that I can log into another account and my information is kept private. | Given I am currently logged in, when I click the log out button, then I should be brought to the login page. |  |  | Pass |  | Pass | AP 4/4
| Given I am not logged in, when I want to log out then there should not be a log out button displayed. |  |  | Pass |  | Pass | AP 4/4
As a buyer, I want to check out the products in my shopping cart so that I can buy all of the products that I want at once. | Given I am in my shopping cart when I want to check out then there should be a check out button that will check me out. |  |  | Pass |  | Pass | AP 4/4
| Given I have clicked the checkout button when the items have been purchased then they should decrease in quantity accordingly. |  |  | Fail | Quantity does not decrease. | Pass | AP 4/4; once items are purchased the quantity is appropriately updated in the inventory.
| Given there are no products in my shopping cart when I am in my shopping cart then the button to check out will be disabled. |  |  | Pass |  | Pass | AP 4/4; button to check out does not appear when cart is empty.
| Given there are items in my cart when I click the checkout button then the items should be removed from my cart. |  |  | Pass |  | Pass | AP 4/4
As an owner I want to update the product quantity when someone has purchased an item so that I can keep track of what is being sold and what is not. | Given a user can check out with their shopping cart when the products are purchased then the products will decrement depending on how many were purchased. |  |  | Fail | Quantity does not decrease. | Pass | AP 4/4
| GIVEN the quantity of one or more candles in the cart is greater than the quantity in the inventory WHEN a user tries to check out THEN the user will be unable to check out and an error message will be displayed. |  |  |  |  | Pass | AP 4/4
As a customer I want to create a password with my account so that I can protect my login information. | Given I am on the login page when I enter my username and password then I will be brought to the product list. |  |  |  |  | Pass | AP 4/4
| Given I am on the login page when I enter the wrong password for a given username then I will not be brought to the product list until I enter the proper one. |  |  |  |  | Pass | AP 4/4; error message displays and blocks login.
| Given I am on the login page when I enter a username that doesn't exist then I will be brought to the user signup page. |  |  |  |  | Pass | AP 4/4
| Given I am on the user signup page when I enter a password that doesn't match the criteria (numbers, letters, special chars, etc.) then I will be unable to sign up and a message will display telling me what to fix. |  |  |  |  | Pass | AP 4/4
| Given I am on the user signup page when I enter a username that already exists then I will be unable to sign up and an error will display. |  |  |  |  | Pass | AP 4/4
As a customer I want to be able to add a credit card so that I can carry out my purchases. | Given I am on the checkout page when I want to cash out then there will be a button to add a credit card to my account. |  |  |  |  | Pass | AP 4/4
| Given I am on the checkout page when I click on the credit card button then a new page will be brought up with fields to fill out my credit card. |  |  |  |  | Pass | AP 4/4